## Slide 1
TEAM LEAD IMPLEMENTATION BRIEFING
Phased Sprint
Delivery Plan
Governance model for the Applications Development / SharePoint team
USAMRIID Information Management Division | Contract No. HT9425-23-F-0002 NexTech LinTech LLC | Draft Version 3.0, July 2026
Prepared by Chhoeun Groleau and Mike Maurer

## Slide 2
EXECUTIVE SUMMARY
Plan at a Glance
A governance model with two operating levels, a clear escalation path, and disciplined scope control — built for the Applications Development / SharePoint team.
2
Operating levels
Program & Team
3
ADO work tiers
Epic → Feature → Story
4
Governance reviews
Daily to Monthly
5
Step change
control process
KEY TAKEAWAYS FOR TEAM LEADS
Escalate risks and blockers immediately — early communication gives the team options
Keep ADO boards current daily; they are the single source of truth for the program
No new epics or sprint-level scope changes without Government Lead approval
Weekly Governance Review, bi-weekly Program Review, monthly Government Status Review
Complete required Azure DevOps and Agile training modules — most due within 30 days; some self-paced
Executive Summary
USAMRIID IMD | HT9425-23-F-0002

## Slide 3
SECTION 1
Purpose and Scope
This plan is the team's operational guide for rolling out the Phased Sprint Delivery Plan governance model across the USAMRIID contract, for the Applications Development / SharePoint team.
WHAT THIS PLAN COVERS
How the model works and why it matters
Roles and responsibilities for PMs, Team Leads, and Developers
Azure DevOps board standards and daily expectations
Governance review cadence
Scope management and change control process
Risk escalation expectations and training requirements
INITIAL ROLLOUT
Applications Development /
SharePoint Team
Two operating levels, working together:
P
Program Level — contract deliverables, milestones, government reporting
T
Team Level — sprint execution, backlog, day-to-day delivery
Full detail on the two-level model follows on the next slide.
Purpose and Scope
USAMRIID IMD | HT9425-23-F-0002

## Slide 4
SECTION 2
How the Model Works
Two levels operating simultaneously — complementary layers that answer different questions, not competing systems.
PROGRAM LEVEL
Managed by the Program Manager
• Contract deliverables
• Program milestones
• Government reporting
• Risk management
• Scope adherence
“Are we delivering the agreed-upon outcomes?”
TEAM LEVEL (AGILE)
Managed by Team Leads
• Sprint execution & standups
• Schedule adherence
• Change control
• Backlog prioritization
• Work item tracking
• Technical reviews & defect management
“How are we completing the work?”
How the Model Works
USAMRIID IMD | HT9425-23-F-0002

## Slide 5
SECTION 2
Azure DevOps Work Hierarchy
Every stakeholder must be able to trace work back to a program objective.
EPIC
Contract deliverables, major program objectives, government priorities
e.g. Application Modernization, Security Compliance Enhancements
Government Lead reviews
FEATURE
Major capabilities, functional requirements, planned releases
e.g. User Authentication, Dashboard Reporting, Audit Logging
Team Leads manage progress
USER STORY / WORK ITEM
Individual development tasks, enhancements, defects, technical work
e.g. Add MFA, Fix dashboard filter, Create audit log export
Developers own daily
Azure DevOps Work Hierarchy
USAMRIID IMD | HT9425-23-F-0002

## Slide 6
SECTION 3
The Team Lead Role
Your three core areas of operational responsibility under this model.
!
Communication
& Escalation
• Escalate blockers, scope concerns, and technical risks immediately — not at the next status meeting
• Early communication gives the team options; late communication creates emergencies
≡
Board & Scope
Management
• Weekly ADO board health and backlog reviews
• No new epics or sprint-level scope changes without Government Lead approval
• Ensure acceptance criteria exist before work enters development
✓
Training &
Coaching
• Reinforce Delivery principles in standups through practical application
• Participate in weekly Team Lead Governance Review
The Team Lead Role
USAMRIID IMD | HT9425-23-F-0002

## Slide 7
SECTION 4
Daily Standup — Purpose and Expectations
Standups are already in place. This reinforces the intent and expected behavior.
✓
A STANDUP IS
• A team coordination meeting
• A forum to surface blockers early
• The place to identify risks before they affect delivery
• A place to flag dependencies and constraints
✗
A STANDUP IS NOT
• A status report to management
• A meeting to explain completed work in detail
• A performance evaluation
• Optional — attendance and honesty are expected
Key Message: If you believe a task may miss a target date, become blocked, or require more effort than planned — say so immediately.
Daily Standup
USAMRIID IMD | HT9425-23-F-0002

## Slide 8
SECTION 5
Azure DevOps Board Standards
ADO is the single source of truth for all work on this contract. Board accuracy is not optional.
BACKLOG
Approved, prioritized work not yet started
IN PROGRESS
Actively being worked — updated daily
IN REVIEW
Code complete — awaiting review or testing
DONE
Accepted, verified complete
Two-tier structure: the workflow above is for status reporting; each feature also has a task-level board (Backlog → In Progress → Done, with a Blocked flag) for day-to-day tracking.
WORK ITEM UPDATE RULES
Update frequency
Every business day — not end of sprint
Blocker documentation
Same day the blocker is identified
Column movement
Move as soon as status actually changes
Acceptance criteria
Defined before a work item moves to In Progress
Aging items
In Progress > 5 business days without update → escalate to Team Lead
ADO Board Standards
USAMRIID IMD | HT9425-23-F-0002

## Slide 9
SECTION 6
Governance Review Cadence
Standing commitments, not ad hoc events.
FREQUENCY
REVIEW
ATTENDEES
FOCUS
DAILY
Team Standup
All team members
Blockers, risks, daily coordination
BI-WEEKLY
Program Review
PM, Team Leads, Technical Leads, Government POC
Epic/Feature progress, risks, resource concerns, upcoming deliverables
MONTHLY
Government Status Review
PM, Team Leads, Government POC
Major accomplishments, deliverable status, risk awareness, planned activities
ADO dashboards and reports are the primary visual aid for bi-weekly and monthly reviews. Ensure your board is current before each review.
Governance Review Cadence
USAMRIID IMD | HT9425-23-F-0002

## Slide 10
SECTION 7
Scope Management & Change Control
Scope discipline is non-negotiable. Every code change is a change request.
1
Document
Add to ADO backlog: requestor, description, date, estimate
2
Assess
Team Lead evaluates schedule/resource impact — no verbal approvals
3
Review
Team Lead brings assessment to Government Lead
4
Decision
Government Lead approves, defers, or rejects within 2 business days — documented in ADO
5
Execute
Backlog/sprint updated; work begins only after this step
No work begins on Major efforts until Step 4 is complete and documented — regardless of requester seniority or urgency claims.
DEVELOPER TIME ALLOCATION PER SPRINT
50%
25%
25%
Major work efforts
Minor work efforts
Meetings & admin
Scope Management & Change Control
USAMRIID IMD | HT9425-23-F-0002

## Slide 11
SECTION 8
Risk and Escalation Framework
Risks must be communicated as soon as they are identified — not at the next scheduled meeting.
⏱
Schedule Risk
Missed milestones, potential delays, resource shortages
ESCALATE TO
Team Lead → Gov't TPOC, PM
⚙
Technical Risk
Architectural concerns, security issues, significant defects
ESCALATE TO
Team Lead → Gov't TPOC, PM
▢
Scope Risk
Unplanned work requests, requirement changes, expanding requirements
ESCALATE TO
Team Lead → Gov't TPOC, PM
⛓
Dependency Risk
External approvals pending, third-party access, GFE/PIV constraints
ESCALATE TO
Team Lead → Gov't TPOC, PM
Risk and Escalation Framework
USAMRIID IMD | HT9425-23-F-0002

## Slide 12
SECTION 9
Metrics We Will Track
Not punitive — leading indicators of whether the process is working.
DELIVERY
Work completed per sprint, work in progress, backlog size, sprint completion rate
QUALITY
Defect trends, rework items, review cycle times
PROCESS
Blocked items and aging time, ADO update compliance, training completion rates
PROGRAM
Deliverable completion status, milestone achievement, scope change volume, risk trends
Metrics We Will Track
USAMRIID IMD | HT9425-23-F-0002

## Slide 13
SECTION 10
Training Recommendations
Every module below is free to access
TRAINING MODULE
SOURCE
AUDIENCE
TARGET
Azure DevOps: Work Item Management
Microsoft Learn (free)
All developers
30 days
Azure DevOps: Backlog and Sprint Management
Microsoft Learn (free)
Developers + Team Leads
30 days
Free Agile Courses Library
Udemy (free)
All team members
Self-paced
Azure DevOps Boards Fundamentals
YouTube (free)
All developers
30 days
Azure DevOps Zero to Hero
Microsoft Learn (free)
Developers + Team Leads
Self-paced
Agile Scrum Full Course (4 Hours)
YouTube (free)
All team members
Self-paced
Scrum Fundamentals — Short Intro
YouTube (free)
All team members
30 days
All modules are free to access in full; no login, subscription, or certificate purchase required.
Training Requirements
USAMRIID IMD | HT9425-23-F-0002
Notes: Training source links (per Phased Sprint Delivery Plan, Rev. 07/21/2026, Section 10): 1. Azure DevOps: Work Item Management (Microsoft Learn): https://learn.microsoft.com/en-us/azure/devops/boards/backlogs/manage-work-items?view=azure-devops - fully free, no account tier required. Audience: All developers. Target: 30 days. 2. Azure DevOps: Backlog and Sprint Management (Microsoft Learn): https://learn.microsoft.com/en-us/azure/devops/boards/backlogs/backlogs-overview?view=azure-devops - fully free. Audience: Developers + Team Leads. Target: 30 days. 3. Free Agile Courses Library (Udemy): https://www.udemy.com/topic/agile/free/ - free, multi-topic library. Audience: All team members. Target: Self-paced. 4. Azure DevOps Boards Fundamentals (YouTube - Complete Azure DevOps Boards Training for Beginners): https://www.youtube.com/watch?v=rXwUSCDH59Y - Audience: All developers. Target: 30 days. 5. Azure DevOps Zero to Hero - full walkthrough of Boards, Repos, Pipelines: https://learn.microsoft.com/en-us/shows/devops-lab/azure-devops-zero-to-hero-tutorial - Audience: Developers + Team Leads. Target: Self-paced. 6. Agile Scrum Full Course in 4 Hours (Simplilearn, YouTube): https://www.youtube.com/watch?v=VFQtSqChlsk - Audience: All team members. Target: Self-paced. 7. Scrum Fundamentals - Scrum 101: The Fundamentals of the Agile Scrum Methodology (YouTube): https://www.youtube.com/watch?v=ojpTDcdm0vQ - Audience: All team members. Target: 30 days.

## Slide 14
SECTION 11
What Success Looks Like
✓
Risks and blockers are identified and communicated before they affect delivery
✓
ADO boards reflect accurate, current status at any point in time without prompting
✓
No work begins on unapproved requests — scope discipline is maintained
✓
Sprint completion rates are predictable and schedule surprises are rare
✓
Government stakeholders have clear, data-driven visibility into project health
✓
Team Leads and developers understand not just how, but why these practices exist
Success is a shared understanding of priorities, progress, risks, and expected outcomes — across leadership, team leads, developers, and government stakeholders.
Questions about this plan should be directed to the Program Manager. This document will be reviewed and updated as the program evolves.